## Sheet1
No. | Elapsed Time | Tasks | Milestones | Chapters/Deliverables
1 | Week 1 | Timeline of FYP-II, Develop Locations data generation app, Introduction Chapter |  | Timeline
2 | Week 2 | Data Balancing | Get equivalent data for each feature | Chapter 1
3 | Week 3 | Feature Selection, Literature Review | Select feature to be used
4 | Week 4 | Formulate Objective and Fitness Functions | Design objective and fitness functions | Objective and Fitness Functions, Chapter 2
5 | Week 5 | Design Optimization Algorithm: Framework Design, Project plan and initial design
6 | Week 6 | Design Optimization Algorithm: Reference point generation |  | Chapter 3
7 | Week 7 | Design Optimization Algorithm: Optimization Module, Design and specification | Design Optimization Algorithm | Optimization Algorithm
8 | Week 8 | Algorithm Implementation | Develop an API for the optimization algorithm | Chapter 4
9 | Week 9 | Experiments and Result Analysis, System Development | Test the performance of the algorithm
10 | Week 10 | Demonstration App Design | Design the interface of the demo app | UI Design, Chapter 5
11 | Week 11 | Demonstration App Development, Result Analysis and Testing | Develop the backend of the demonstration app
12 | Week 12 | Demonstration App Testing | Test the performance of demo app | Demonstration App, Chapter 6
13 | Week 13 | Conclusion | Project conclusion and future enhancement
14 | Week 14 | Project Finalization | Project Completion | Project, Chapter 7